## Overview
NDMA KnowledgeWeb
Mandera–Wajir Cross-border Peace & Water
NDMA/DRM/2023/007 • Published
Generated 24 Aug 2026 10:56 UTC • by Public portal
Project overview
Field | Value
Project name | Mandera–Wajir Cross-border Peace & Water
Serial no. | NDMA/DRM/2023/007
Tender no. | —
Status | Published
Project manager | H. Noor
Funding agreement | —
Start date | 2023-03-01
End date | 2025-02-28
Duration | 2 years
Total budget (KSh) | 165000000
Results progress (%) | 44.2
Funds absorption (%) | 40
Partner investment | No
Stalled | No
Description | Shared water points, boreholes and community peace committees along the Mandera–Wajir border corridor.

## Results Framework
NDMA KnowledgeWeb
Mandera–Wajir Cross-border Peace & Water
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 10:56 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2022/23 | Q1 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2022/23 | Q2 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2022/23 | Q3 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2022/23 | Q4 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2023/24 | Q1 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2023/24 | Q2 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2023/24 | Q3 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Peace committees established and active | committees | 0 | 2023/24 | Q4 | 7.5 | 3 | 40 | Behind
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2022/23 | Q1 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2022/23 | Q2 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2022/23 | Q3 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2022/23 | Q4 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2023/24 | Q1 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2023/24 | Q2 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2023/24 | Q3 | 6 | 3 | 50 | At risk
Community peace structures strengthened | Cross-border dialogue forums held | forums | 0 | 2023/24 | Q4 | 6 | 3 | 50 | At risk
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2022/23 | Q1 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2022/23 | Q2 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2022/23 | Q3 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2022/23 | Q4 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2023/24 | Q1 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2023/24 | Q2 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2023/24 | Q3 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Shared resource-use agreements brokered | agreements | 0 | 2023/24 | Q4 | 5 | 2 | 40 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2022/23 | Q1 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2022/23 | Q2 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2022/23 | Q3 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2022/23 | Q4 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2023/24 | Q1 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2023/24 | Q2 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2023/24 | Q3 | 15 | 7 | 46.7 | Behind
Conflict-sensitive resource sharing improved | Early-warning conflict alerts responded to | alerts | 0 | 2023/24 | Q4 | 15 | 7 | 46.7 | Behind
Overall results progress: 44.2% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Mandera–Wajir Cross-border Peace & Water
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 10:56 UTC • by Public portal
Counties
County | Sub-county | Ward
Mandera | — | —
Wajir | — | —
Sectors
Sector
Peace & Security
Water & Sanitation
Implementers
Organization
Kenya Red Cross Society
NDMA
Beneficiaries
Group | Targeted | Reached
Agro-pastoralists | 25000 | 12000

## Financing
NDMA KnowledgeWeb
Mandera–Wajir Cross-border Peace & Water
Funding sources and county allocations
Generated 24 Aug 2026 10:56 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
European Union | 150000000 | Cross-border facility
Total committed: KSh 150,000,000 • Project budget: KSh 165,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Mandera | 2023/24 | 165000000