## Overview
NDMA KnowledgeWeb
Turkana Integrated Water Resilience Programme
NDMA/DRM/2021/018 • Published
Generated 11 Oct 2026 10:55 UTC • by Public portal
Project overview
Field | Value
Project name | Turkana Integrated Water Resilience Programme
Serial no. | NDMA/DRM/2021/018
Tender no. | —
Status | Published
Project manager | J. Ekiru
Funding agreement | —
Start date | 2021-08-01
End date | 2024-07-31
Duration | 3 years
Total budget (KSh) | 480000000
Results progress (%) | 94
Funds absorption (%) | 78
Partner investment | No
Stalled | No
Description | Boreholes, water pans and last-mile reticulation for drought-affected communities across Turkana.

## Results Framework
NDMA KnowledgeWeb
Turkana Integrated Water Resilience Programme
Outputs → indicators → targets & achievements
Generated 11 Oct 2026 10:55 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q1 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q2 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q3 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q4 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q1 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q2 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q3 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q4 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q4 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q4 | 2 | 2 | 100 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q1 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q2 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q3 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q4 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q1 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q2 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q3 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q4 | 15000 | 12900 | 86 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q1 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q2 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q3 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q4 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q1 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q2 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q3 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q4 | 10 | 9 | 90 | On track
Overall results progress: 94.0% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Turkana Integrated Water Resilience Programme
Counties, sectors, implementers and beneficiaries
Generated 11 Oct 2026 10:55 UTC • by Public portal
Counties
County | Sub-county | Ward
Turkana | — | —
Sectors
Sector
Water & Sanitation
Implementers
Organization
Ministry of Water & Sanitation
NDMA
Beneficiaries
Group | Targeted | Reached
Pastoralist households | 120000 | 96000

## Financing
NDMA KnowledgeWeb
Turkana Integrated Water Resilience Programme
Funding sources and county allocations
Generated 11 Oct 2026 10:55 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
World Bank | 300000000 | IDA credit
National Treasury (GoK) | 180000000 | GoK counterpart
Total committed: KSh 480,000,000 • Project budget: KSh 480,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Turkana | 2021/22 | 240000000
Turkana | 2022/23 | 240000000