## Overview
NDMA KnowledgeWeb
Baringo Community Water Pans
NDMA/DRM/2020/011 • Published
Generated 11 Oct 2026 11:24 UTC • by Public portal
Project overview
Field | Value
Project name | Baringo Community Water Pans
Serial no. | NDMA/DRM/2020/011
Tender no. | —
Status | Published
Project manager | C. Chelimo
Funding agreement | —
Start date | 2020-07-15
End date | 2023-06-30
Duration | 2 years 11 months
Total budget (KSh) | 95000000
Results progress (%) | 96
Funds absorption (%) | 88
Partner investment | No
Stalled | No
Description | Excavation and lining of community water pans with solar pumping.

## Results Framework
NDMA KnowledgeWeb
Baringo Community Water Pans
Outputs → indicators → targets & achievements
Generated 11 Oct 2026 11:24 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q1 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q2 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q3 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q4 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q1 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q2 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q3 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q4 | 15000 | 14100 | 94 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q1 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q2 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q3 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q4 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q1 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q2 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q3 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q4 | 10 | 9 | 90 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q1 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q2 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q3 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q4 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q1 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q2 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q3 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q4 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q4 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q4 | 2 | 2 | 100 | On track
Overall results progress: 96.0% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Baringo Community Water Pans
Counties, sectors, implementers and beneficiaries
Generated 11 Oct 2026 11:24 UTC • by Public portal
Counties
County | Sub-county | Ward
Baringo | — | —
Sectors
Sector
Water & Sanitation
Implementers
Organization
Ministry of Water & Sanitation
Beneficiaries
Group | Targeted | Reached
Pastoralist households | 30000 | 28000

## Financing
NDMA KnowledgeWeb
Baringo Community Water Pans
Funding sources and county allocations
Generated 11 Oct 2026 11:24 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
National Treasury (GoK) | 95000000 | —
Total committed: KSh 95,000,000 • Project budget: KSh 95,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Baringo | 2020/21 | 95000000