## Overview
NDMA KnowledgeWeb
Tana River Flood Resilience & Access
NDMA/DRM/2022/003 • Published
Generated 24 Aug 2026 11:58 UTC • by Public portal
Project overview
Field | Value
Project name | Tana River Flood Resilience & Access
Serial no. | NDMA/DRM/2022/003
Tender no. | —
Status | Published
Project manager | D. Komora
Funding agreement | —
Start date | 2022-08-20
End date | 2025-07-31
Duration | 2 years 11 months
Total budget (KSh) | 260000000
Results progress (%) | 55.3
Funds absorption (%) | 48
Partner investment | No
Stalled | No
Description | Flood dykes, raised access roads and early-warning for displaced communities.

## Results Framework
NDMA KnowledgeWeb
Tana River Flood Resilience & Access
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 11:58 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q1 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q2 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q3 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q4 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q1 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q2 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q3 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q4 | 3 | 2 | 66.7 | At risk
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q1 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q2 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q3 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q4 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q1 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q2 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q3 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q4 | 4.5 | 2 | 44.4 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q1 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q2 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q3 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q4 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q1 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q2 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q3 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q4 | 1250 | 688 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q1 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q2 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q3 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q4 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q1 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q2 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q3 | 50000 | 27500 | 55 | At risk
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q4 | 50000 | 27500 | 55 | At risk
Overall results progress: 55.3% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Tana River Flood Resilience & Access
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 11:58 UTC • by Public portal
Counties
County | Sub-county | Ward
Tana River | — | —
Sectors
Sector
Environment & NRM
Roads & Infrastructure
Implementers
Organization
World Vision
NDMA
Beneficiaries
Group | Targeted | Reached
Internally displaced persons | 12000 | 8000

## Financing
NDMA KnowledgeWeb
Tana River Flood Resilience & Access
Funding sources and county allocations
Generated 24 Aug 2026 11:58 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
African Development Bank | 260000000 | —
Total committed: KSh 260,000,000 • Project budget: KSh 260,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Tana River | 2023/24 | 260000000