## Overview
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
NDMA/DRM/2022/016 • Published
Generated 24 Aug 2026 11:58 UTC • by Public portal
Project overview
Field | Value
Project name | Lower Eastern Sand Dams & Food Security
Serial no. | NDMA/DRM/2022/016
Tender no. | —
Status | Published
Project manager | M. Mutua
Funding agreement | —
Start date | 2022-01-10
End date | 2024-12-31
Duration | 3 years
Total budget (KSh) | 180000000
Results progress (%) | 80.7
Funds absorption (%) | 70
Partner investment | No
Stalled | No
Description | Sand dams, shallow wells and conservation agriculture across Kitui and Makueni.

## Results Framework
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 11:58 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q1 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q2 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q3 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q4 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q1 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q2 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q3 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q4 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q4 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q4 | 2 | 2 | 100 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q1 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q2 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q3 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q4 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q1 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q2 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q3 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q4 | 15000 | 11400 | 76 | At risk
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q1 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q2 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q3 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q4 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q1 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q2 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q3 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q4 | 10 | 8 | 80 | On track
Overall results progress: 80.7% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 11:58 UTC • by Public portal
Counties
County | Sub-county | Ward
Kitui | — | —
Makueni | — | —
Sectors
Sector
Water & Sanitation
Agriculture & Food Security
Implementers
Organization
Mercy Corps
County Government
Beneficiaries
Group | Targeted | Reached
Smallholder farmers | 26000 | 22000

## Financing
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
Funding sources and county allocations
Generated 24 Aug 2026 11:58 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
European Union | 140000000 | —
National Treasury (GoK) | 40000000 | —
Total committed: KSh 180,000,000 • Project budget: KSh 180,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Kitui | 2022/23 | 90000000
Makueni | 2022/23 | 90000000