## Overview
NDMA KnowledgeWeb
Narok Rural Water Supply Expansion
NDMA/DRM/2019/009 • Published
Generated 24 Aug 2026 12:08 UTC • by Public portal
Project overview
Field | Value
Project name | Narok Rural Water Supply Expansion
Serial no. | NDMA/DRM/2019/009
Tender no. | —
Status | Published
Project manager | S. Nkoitoi
Funding agreement | —
Start date | 2019-12-01
End date | 2022-11-30
Duration | 3 years
Total budget (KSh) | 55000000
Results progress (%) | 95.5
Funds absorption (%) | 90
Partner investment | No
Stalled | No
Description | Piped water expansion and household connections for drought-prone wards.

## Results Framework
NDMA KnowledgeWeb
Narok Rural Water Supply Expansion
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 12:08 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2019/20 | Q1 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2019/20 | Q2 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2019/20 | Q3 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2019/20 | Q4 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q1 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q2 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q3 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2020/21 | Q4 | 3 | 3 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2019/20 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2019/20 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2019/20 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2019/20 | Q4 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2020/21 | Q4 | 2 | 2 | 100 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2019/20 | Q1 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2019/20 | Q2 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2019/20 | Q3 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2019/20 | Q4 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q1 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q2 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q3 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2020/21 | Q4 | 15000 | 13800 | 92 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2019/20 | Q1 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2019/20 | Q2 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2019/20 | Q3 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2019/20 | Q4 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q1 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q2 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q3 | 10 | 9 | 90 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2020/21 | Q4 | 10 | 9 | 90 | On track
Overall results progress: 95.5% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Narok Rural Water Supply Expansion
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 12:08 UTC • by Public portal
Counties
County | Sub-county | Ward
Narok | — | —
Sectors
Sector
Water & Sanitation
Implementers
Organization
Ministry of Water & Sanitation
Beneficiaries
Group | Targeted | Reached
Pastoralist households | 17000 | 16000

## Financing
NDMA KnowledgeWeb
Narok Rural Water Supply Expansion
Funding sources and county allocations
Generated 24 Aug 2026 12:08 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
National Treasury (GoK) | 55000000 | —
Total committed: KSh 55,000,000 • Project budget: KSh 55,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Narok | 2019/20 | 55000000