## Overview
NDMA KnowledgeWeb
Wajir Maternal & Child Nutrition
NDMA/DRM/2020/033 • Published
Generated 24 Aug 2026 12:02 UTC • by Public portal
Project overview
Field | Value
Project name | Wajir Maternal & Child Nutrition
Serial no. | NDMA/DRM/2020/033
Tender no. | —
Status | Published
Project manager | S. Mohamed
Funding agreement | —
Start date | 2020-09-01
End date | 2023-08-31
Duration | 3 years
Total budget (KSh) | 145000000
Results progress (%) | 89.9
Funds absorption (%) | 85
Partner investment | No
Stalled | No
Description | Integrated management of acute malnutrition and outreach nutrition services.

## Results Framework
NDMA KnowledgeWeb
Wajir Maternal & Child Nutrition
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 12:02 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2020/21 | Q1 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2020/21 | Q2 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2020/21 | Q3 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2020/21 | Q4 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2021/22 | Q1 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2021/22 | Q2 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2021/22 | Q3 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children screened for acute malnutrition | children | 0 | 2021/22 | Q4 | 22500 | 20250 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2020/21 | Q1 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2020/21 | Q2 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2020/21 | Q3 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2020/21 | Q4 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2021/22 | Q1 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2021/22 | Q2 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2021/22 | Q3 | 3000 | 2700 | 90 | On track
Nutrition services scaled up | Children admitted to therapeutic feeding | children | 0 | 2021/22 | Q4 | 3000 | 2700 | 90 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2020/21 | Q1 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2020/21 | Q2 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2020/21 | Q3 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2020/21 | Q4 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2021/22 | Q1 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2021/22 | Q2 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2021/22 | Q3 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Health facilities supported with supplies | facilities | 0 | 2021/22 | Q4 | 11.25 | 10 | 88.9 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2020/21 | Q1 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2020/21 | Q2 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2020/21 | Q3 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2020/21 | Q4 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2021/22 | Q1 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2021/22 | Q2 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2021/22 | Q3 | 75 | 68 | 90.7 | On track
Health system drought-resilience strengthened | Community health volunteers trained | volunteers | 0 | 2021/22 | Q4 | 75 | 68 | 90.7 | On track
Overall results progress: 89.9% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Wajir Maternal & Child Nutrition
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 12:02 UTC • by Public portal
Counties
County | Sub-county | Ward
Wajir | — | —
Sectors
Sector
Health & Nutrition
Implementers
Organization
NDMA
County Government
Beneficiaries
Group | Targeted | Reached
Children under 5 | 60000 | 52000
Women & girls | 24000 | 21000

## Financing
NDMA KnowledgeWeb
Wajir Maternal & Child Nutrition
Funding sources and county allocations
Generated 24 Aug 2026 12:02 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
UNICEF | 130000000 | —
Total committed: KSh 130,000,000 • Project budget: KSh 145,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Wajir | 2021/22 | 145000000