## Overview
NDMA KnowledgeWeb
Laikipia Rangeland Water & Livestock
NDMA/DRM/2022/058 • Published
Generated 11 Oct 2026 11:28 UTC • by Public portal
Project overview
Field | Value
Project name | Laikipia Rangeland Water & Livestock
Serial no. | NDMA/DRM/2022/058
Tender no. | —
Status | Published
Project manager | W. Kimani
Funding agreement | —
Start date | 2022-04-05
End date | 2024-09-30
Duration | 2 years 6 months
Total budget (KSh) | 80000000
Results progress (%) | 81.4
Funds absorption (%) | 72
Partner investment | No
Stalled | No
Description | Water troughs, boreholes and holistic grazing on group ranches.

## Results Framework
NDMA KnowledgeWeb
Laikipia Rangeland Water & Livestock
Outputs → indicators → targets & achievements
Generated 11 Oct 2026 11:28 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q1 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q2 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q3 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2021/22 | Q4 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q1 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q2 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q3 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | People with new access to safe water | people | 0 | 2022/23 | Q4 | 15000 | 11850 | 79 | At risk
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q1 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q2 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q3 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2021/22 | Q4 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q1 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q2 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q3 | 10 | 8 | 80 | On track
Communities with sustained access to safe water | Water management committees trained | committees | 0 | 2022/23 | Q4 | 10 | 8 | 80 | On track
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q1 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q2 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q3 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2021/22 | Q4 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q1 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q2 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q3 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Boreholes drilled and equipped | boreholes | 0 | 2022/23 | Q4 | 3 | 2 | 66.7 | At risk
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2021/22 | Q4 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q1 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q2 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q3 | 2 | 2 | 100 | On track
Water supply infrastructure constructed and operational | Water pans and earth dams rehabilitated | pans | 0 | 2022/23 | Q4 | 2 | 2 | 100 | On track
Overall results progress: 81.4% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Laikipia Rangeland Water & Livestock
Counties, sectors, implementers and beneficiaries
Generated 11 Oct 2026 11:28 UTC • by Public portal
Counties
County | Sub-county | Ward
Laikipia | — | —
Sectors
Sector
Water & Sanitation
Livestock
Implementers
Organization
Kenya Red Cross Society
Beneficiaries
Group | Targeted | Reached
Agro-pastoralists | 11000 | 9500

## Financing
NDMA KnowledgeWeb
Laikipia Rangeland Water & Livestock
Funding sources and county allocations
Generated 11 Oct 2026 11:28 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
National Treasury (GoK) | 60000000 | —
Kenya Red Cross | 20000000 | —
Total committed: KSh 80,000,000 • Project budget: KSh 80,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Laikipia | 2022/23 | 80000000