## Overview
NDMA KnowledgeWeb
Makueni Fruit Value-Chain Development
NDMA/DRM/2020/027 • Published
Generated 12 Oct 2026 18:04 UTC • by Public portal
Project overview
Field | Value
Project name | Makueni Fruit Value-Chain Development
Serial no. | NDMA/DRM/2020/027
Tender no. | —
Status | Published
Project manager | J. Nzioka
Funding agreement | —
Start date | 2020-10-01
End date | 2023-09-30
Duration | 3 years
Total budget (KSh) | 120000000
Results progress (%) | 86.8
Funds absorption (%) | 80
Partner investment | No
Stalled | No
Description | Mango and drought-tolerant fruit aggregation, cold storage and market access.

## Results Framework
NDMA KnowledgeWeb
Makueni Fruit Value-Chain Development
Outputs → indicators → targets & achievements
Generated 12 Oct 2026 18:04 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2020/21 | Q1 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2020/21 | Q2 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2020/21 | Q3 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2020/21 | Q4 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q1 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q2 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q3 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q4 | 5000 | 4400 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2020/21 | Q1 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2020/21 | Q2 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2020/21 | Q3 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2020/21 | Q4 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q1 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q2 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q3 | 375 | 330 | 88 | On track
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q4 | 375 | 330 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2020/21 | Q1 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2020/21 | Q2 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2020/21 | Q3 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2020/21 | Q4 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q1 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q2 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q3 | 4500 | 3960 | 88 | On track
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q4 | 4500 | 3960 | 88 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2020/21 | Q1 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2020/21 | Q2 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2020/21 | Q3 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2020/21 | Q4 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q1 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q2 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q3 | 6 | 5 | 83.3 | On track
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q4 | 6 | 5 | 83.3 | On track
Overall results progress: 86.8% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Makueni Fruit Value-Chain Development
Counties, sectors, implementers and beneficiaries
Generated 12 Oct 2026 18:04 UTC • by Public portal
Counties
County | Sub-county | Ward
Makueni | — | —
Sectors
Sector
Agriculture & Food Security
Implementers
Organization
County Government
FAO
Beneficiaries
Group | Targeted | Reached
Smallholder farmers | 20000 | 18000

## Financing
NDMA KnowledgeWeb
Makueni Fruit Value-Chain Development
Funding sources and county allocations
Generated 12 Oct 2026 18:04 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
World Bank | 120000000 | —
Total committed: KSh 120,000,000 • Project budget: KSh 120,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Makueni | 2021/22 | 120000000