## Overview
NDMA KnowledgeWeb
Tana Delta Irrigated Agriculture Scheme
NDMA/DRM/2021/052 • Published
Generated 11 Oct 2026 11:30 UTC • by Public portal
Project overview
Field | Value
Project name | Tana Delta Irrigated Agriculture Scheme
Serial no. | NDMA/DRM/2021/052
Tender no. | —
Status | Published
Project manager | F. Abdi
Funding agreement | —
Start date | 2021-11-01
End date | 2024-10-31
Duration | 3 years
Total budget (KSh) | 300000000
Results progress (%) | 67.7
Funds absorption (%) | 60
Partner investment | No
Stalled | No
Description | Smallholder irrigation and drought-tolerant seed along the Tana river system.

## Results Framework
NDMA KnowledgeWeb
Tana Delta Irrigated Agriculture Scheme
Outputs → indicators → targets & achievements
Generated 11 Oct 2026 11:30 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q1 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q2 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q3 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2021/22 | Q4 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q1 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q2 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q3 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q4 | 5000 | 3400 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q1 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q2 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q3 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2021/22 | Q4 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q1 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q2 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q3 | 375 | 255 | 68 | At risk
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q4 | 375 | 255 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q1 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q2 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q3 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2021/22 | Q4 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q1 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q2 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q3 | 4500 | 3060 | 68 | At risk
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q4 | 4500 | 3060 | 68 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q1 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q2 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q3 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2021/22 | Q4 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q1 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q2 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q3 | 6 | 4 | 66.7 | At risk
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q4 | 6 | 4 | 66.7 | At risk
Overall results progress: 67.7% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Tana Delta Irrigated Agriculture Scheme
Counties, sectors, implementers and beneficiaries
Generated 11 Oct 2026 11:30 UTC • by Public portal
Counties
County | Sub-county | Ward
Garissa | — | —
Tana River | — | —
Sectors
Sector
Agriculture & Food Security
Implementers
Organization
World Vision
FAO
Beneficiaries
Group | Targeted | Reached
Smallholder farmers | 18000 | 15500

## Financing
NDMA KnowledgeWeb
Tana Delta Irrigated Agriculture Scheme
Funding sources and county allocations
Generated 11 Oct 2026 11:30 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
World Bank | 200000000 | —
USAID | 90000000 | —
Total committed: KSh 290,000,000 • Project budget: KSh 300,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Garissa | 2022/23 | 150000000
Tana River | 2022/23 | 150000000