## Overview
NDMA KnowledgeWeb
West Pokot Agro-forestry & Soil Cover
NDMA/DRM/2023/044 • Approved
Generated 24 Aug 2026 12:11 UTC • by Public portal
Project overview
Field | Value
Project name | West Pokot Agro-forestry & Soil Cover
Serial no. | NDMA/DRM/2023/044
Tender no. | —
Status | Approved
Project manager | R. Cheptoo
Funding agreement | —
Start date | 2023-02-01
End date | 2025-12-31
Duration | 2 years 11 months
Total budget (KSh) | 95000000
Results progress (%) | 39.1
Funds absorption (%) | 36
Partner investment | No
Stalled | No
Description | Agro-forestry, terracing and drought-tolerant crops on degraded slopes.

## Results Framework
NDMA KnowledgeWeb
West Pokot Agro-forestry & Soil Cover
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 12:11 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q1 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q2 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q3 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2022/23 | Q4 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2023/24 | Q1 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2023/24 | Q2 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2023/24 | Q3 | 4500 | 1845 | 41 | Behind
Household food security improved | Households receiving food assistance | households | 0 | 2023/24 | Q4 | 4500 | 1845 | 41 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q1 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q2 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q3 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2022/23 | Q4 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2023/24 | Q1 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2023/24 | Q2 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2023/24 | Q3 | 6 | 2 | 33.3 | Behind
Household food security improved | Cereal banks / grain stores established | stores | 0 | 2023/24 | Q4 | 6 | 2 | 33.3 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q1 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q2 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q3 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2022/23 | Q4 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2023/24 | Q1 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2023/24 | Q2 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2023/24 | Q3 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Farmers adopting drought-tolerant crops | farmers | 0 | 2023/24 | Q4 | 5000 | 2050 | 41 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q1 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q2 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q3 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2022/23 | Q4 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2023/24 | Q1 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2023/24 | Q2 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2023/24 | Q3 | 375 | 154 | 41.1 | Behind
Climate-smart agriculture expanded | Land under small-scale irrigation | acres | 0 | 2023/24 | Q4 | 375 | 154 | 41.1 | Behind
Overall results progress: 39.1% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
West Pokot Agro-forestry & Soil Cover
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 12:11 UTC • by Public portal
Counties
County | Sub-county | Ward
West Pokot | — | —
Sectors
Sector
Agriculture & Food Security
Environment & NRM
Implementers
Organization
Oxfam
Beneficiaries
Group | Targeted | Reached
Smallholder farmers | 14000 | 6000

## Financing
NDMA KnowledgeWeb
West Pokot Agro-forestry & Soil Cover
Funding sources and county allocations
Generated 24 Aug 2026 12:11 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
Danida | 90000000 | —
Total committed: KSh 90,000,000 • Project budget: KSh 95,000,000