## Overview
NDMA KnowledgeWeb
Southern Rangelands Pastoral Education
NDMA/DRM/2021/060 • Published
Generated 24 Aug 2026 12:11 UTC • by Public portal
Project overview
Field | Value
Project name | Southern Rangelands Pastoral Education
Serial no. | NDMA/DRM/2021/060
Tender no. | —
Status | Published
Project manager | N. Sankale
Funding agreement | —
Start date | 2021-09-10
End date | 2024-08-31
Duration | 3 years
Total budget (KSh) | 75000000
Results progress (%) | 64.7
Funds absorption (%) | 58
Partner investment | No
Stalled | No
Description | Mobile schools, bursaries and school-feeding for pastoralist girls.

## Results Framework
NDMA KnowledgeWeb
Southern Rangelands Pastoral Education
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 12:11 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2021/22 | Q1 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2021/22 | Q2 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2021/22 | Q3 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2021/22 | Q4 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2022/23 | Q1 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2022/23 | Q2 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2022/23 | Q3 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Learners benefiting from school meals | learners | 0 | 2022/23 | Q4 | 12500 | 8000 | 64 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2021/22 | Q1 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2021/22 | Q2 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2021/22 | Q3 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2021/22 | Q4 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2022/23 | Q1 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2022/23 | Q2 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2022/23 | Q3 | 15 | 10 | 66.7 | At risk
Access to education sustained during drought | Schools supported with water and sanitation | schools | 0 | 2022/23 | Q4 | 15 | 10 | 66.7 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2021/22 | Q1 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2021/22 | Q2 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2021/22 | Q3 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2021/22 | Q4 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2022/23 | Q1 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2022/23 | Q2 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2022/23 | Q3 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Bursaries awarded to at-risk learners | bursaries | 0 | 2022/23 | Q4 | 1000 | 640 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2021/22 | Q1 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2021/22 | Q2 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2021/22 | Q3 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2021/22 | Q4 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2022/23 | Q1 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2022/23 | Q2 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2022/23 | Q3 | 50 | 32 | 64 | At risk
Retention of vulnerable learners improved | Teachers trained on emergency education | teachers | 0 | 2022/23 | Q4 | 50 | 32 | 64 | At risk
Overall results progress: 64.7% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Southern Rangelands Pastoral Education
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 12:11 UTC • by Public portal
Counties
County | Sub-county | Ward
Kajiado | — | —
Narok | — | —
Sectors
Sector
Education
Implementers
Organization
World Vision
Beneficiaries
Group | Targeted | Reached
Women & girls | 9000 | 7600

## Financing
NDMA KnowledgeWeb
Southern Rangelands Pastoral Education
Funding sources and county allocations
Generated 24 Aug 2026 12:11 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
USAID | 70000000 | —
Total committed: KSh 70,000,000 • Project budget: KSh 75,000,000