## Overview
NDMA KnowledgeWeb
Marsabit Commercial Livestock Off-take
NDMA/DRM/2022/041 • Published
Generated 24 Aug 2026 10:56 UTC • by Public portal
Project overview
Field | Value
Project name | Marsabit Commercial Livestock Off-take
Serial no. | NDMA/DRM/2022/041
Tender no. | —
Status | Published
Project manager | A. Galgalo
Funding agreement | —
Start date | 2022-02-15
End date | 2024-12-31
Duration | 2 years 10 months
Total budget (KSh) | 280000000
Results progress (%) | 70.7
Funds absorption (%) | 65
Partner investment | No
Stalled | No
Description | Drought de-stocking, fodder banks and market linkages for pastoralist herders.

## Results Framework
NDMA KnowledgeWeb
Marsabit Commercial Livestock Off-take
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 10:56 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q1 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q2 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q3 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q4 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2022/23 | Q1 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2022/23 | Q2 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2022/23 | Q3 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2022/23 | Q4 | 100000 | 72000 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q1 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q2 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q3 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q4 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2022/23 | Q1 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2022/23 | Q2 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2022/23 | Q3 | 6250 | 4500 | 72 | At risk
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2022/23 | Q4 | 6250 | 4500 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q1 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q2 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q3 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q4 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2022/23 | Q1 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2022/23 | Q2 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2022/23 | Q3 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2022/23 | Q4 | 3750 | 2700 | 72 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q1 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q2 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q3 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q4 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2022/23 | Q1 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2022/23 | Q2 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2022/23 | Q3 | 7.5 | 5 | 66.7 | At risk
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2022/23 | Q4 | 7.5 | 5 | 66.7 | At risk
Overall results progress: 70.7% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Marsabit Commercial Livestock Off-take
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 10:56 UTC • by Public portal
Counties
County | Sub-county | Ward
Marsabit | — | —
Sectors
Sector
Livestock
Implementers
Organization
FAO
County Government
Beneficiaries
Group | Targeted | Reached
Pastoralist households | 40000 | 34000

## Financing
NDMA KnowledgeWeb
Marsabit Commercial Livestock Off-take
Funding sources and county allocations
Generated 24 Aug 2026 10:56 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
African Development Bank | 220000000 | —
National Treasury (GoK) | 60000000 | —
Total committed: KSh 280,000,000 • Project budget: KSh 280,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Marsabit | 2022/23 | 280000000