## Overview
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
NDMA-DEMO-08 • Published
Generated 24 Aug 2026 11:56 UTC • by Public portal
Project overview
Field | Value
Project name | Lower Eastern Sand Dams & Food Security
Serial no. | NDMA-DEMO-08
Tender no. | —
Status | Published
Project manager | M. Mutua
Funding agreement | —
Start date | 2022-01-10
End date | 2024-12-31
Duration | 3 years
Total budget (KSh) | 180000000
Results progress (%) | 0
Funds absorption (%) | 70
Partner investment | No
Stalled | No
Description | Sand dams, shallow wells and conservation agriculture across Kitui and Makueni.

## Results Framework
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 11:56 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Overall results progress: 0.0% (0 outputs, 0 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 11:56 UTC • by Public portal
Counties
County | Sub-county | Ward
Kitui | — | —
Makueni | — | —
Sectors
Sector
Water & Sanitation
Agriculture & Food Security
Implementers
Organization
Mercy Corps
County Government
Beneficiaries
Group | Targeted | Reached
Smallholder farmers | 26000 | 22000

## Financing
NDMA KnowledgeWeb
Lower Eastern Sand Dams & Food Security
Funding sources and county allocations
Generated 24 Aug 2026 11:56 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
European Union | 140000000 | —
National Treasury (GoK) | 40000000 | —
Total committed: KSh 180,000,000 • Project budget: KSh 180,000,000
County allocations by fiscal year
County | Fiscal year | Amount (KSh)
Kitui | 2022/23 | 90000000
Makueni | 2022/23 | 90000000