## Overview
NDMA KnowledgeWeb
Samburu Livestock Health & Vaccination
NDMA/DRM/2021/074 • Published
Generated 24 Aug 2026 12:07 UTC • by Public portal
Project overview
Field | Value
Project name | Samburu Livestock Health & Vaccination
Serial no. | NDMA/DRM/2021/074
Tender no. | —
Status | Published
Project manager | L. Lekupe
Funding agreement | —
Start date | 2021-05-01
End date | 2024-04-30
Duration | 3 years
Total budget (KSh) | 85000000
Results progress (%) | 81.5
Funds absorption (%) | 75
Partner investment | No
Stalled | No
Description | Community animal health workers, cold chain and mass vaccination campaigns.

## Results Framework
NDMA KnowledgeWeb
Samburu Livestock Health & Vaccination
Outputs → indicators → targets & achievements
Generated 24 Aug 2026 12:07 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2020/21 | Q1 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2020/21 | Q2 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2020/21 | Q3 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2020/21 | Q4 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q1 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q2 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q3 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Households receiving livestock feed support | households | 0 | 2021/22 | Q4 | 3750 | 3075 | 82 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2020/21 | Q1 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2020/21 | Q2 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2020/21 | Q3 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2020/21 | Q4 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q1 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q2 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q3 | 7.5 | 6 | 80 | On track
Pastoral livelihoods protected | Livestock water points rehabilitated | points | 0 | 2021/22 | Q4 | 7.5 | 6 | 80 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2020/21 | Q1 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2020/21 | Q2 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2020/21 | Q3 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2020/21 | Q4 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q1 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q2 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q3 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock vaccinated against priority diseases | animals | 0 | 2021/22 | Q4 | 100000 | 82000 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2020/21 | Q1 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2020/21 | Q2 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2020/21 | Q3 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2020/21 | Q4 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q1 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q2 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q3 | 6250 | 5125 | 82 | On track
Livestock production and health services strengthened | Livestock offtake facilitated during drought | animals | 0 | 2021/22 | Q4 | 6250 | 5125 | 82 | On track
Overall results progress: 81.5% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Samburu Livestock Health & Vaccination
Counties, sectors, implementers and beneficiaries
Generated 24 Aug 2026 12:07 UTC • by Public portal
Counties
County | Sub-county | Ward
Samburu | — | —
Sectors
Sector
Livestock
Implementers
Organization
FAO
Beneficiaries
Group | Targeted | Reached
Pastoralist households | 15000 | 13000

## Financing
NDMA KnowledgeWeb
Samburu Livestock Health & Vaccination
Funding sources and county allocations
Generated 24 Aug 2026 12:07 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
Danida | 85000000 | —
Total committed: KSh 85,000,000 • Project budget: KSh 85,000,000