## Overview
NDMA KnowledgeWeb
Isiolo–Samburu Rangeland Restoration
NDMA/DRM/2023/029 • Published
Generated 11 Oct 2026 11:29 UTC • by Public portal
Project overview
Field | Value
Project name | Isiolo–Samburu Rangeland Restoration
Serial no. | NDMA/DRM/2023/029
Tender no. | —
Status | Published
Project manager | P. Lentoijoni
Funding agreement | —
Start date | 2023-06-15
End date | 2025-06-14
Duration | 2 years
Total budget (KSh) | 120000000
Results progress (%) | 38.4
Funds absorption (%) | 33
Partner investment | No
Stalled | Yes
Description | Reseeding of degraded rangelands, water access and community grazing plans across the Isiolo–Samburu corridor.

## Results Framework
NDMA KnowledgeWeb
Isiolo–Samburu Rangeland Restoration
Outputs → indicators → targets & achievements
Generated 11 Oct 2026 11:29 UTC • by Public portal
Output | Indicator | UoM | Baseline | Fiscal year | Quarter | Target | Achieved | Progress % | Status
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q1 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q2 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q3 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2022/23 | Q4 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q1 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q2 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q3 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Community conservancies supported | conservancies | 0 | 2023/24 | Q4 | 3 | 1 | 33.3 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q1 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q2 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q3 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2022/23 | Q4 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q1 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q2 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q3 | 4.5 | 2 | 44.4 | Behind
Community natural-resource management strengthened | Rangeland management plans developed | plans | 0 | 2023/24 | Q4 | 4.5 | 2 | 44.4 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q1 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q2 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q3 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2022/23 | Q4 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q1 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q2 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q3 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Land rehabilitated and reseeded | hectares | 0 | 2023/24 | Q4 | 1250 | 475 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q1 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q2 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q3 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2022/23 | Q4 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q1 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q2 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q3 | 50000 | 19000 | 38 | Behind
Degraded landscapes restored | Tree seedlings planted and surviving | seedlings | 0 | 2023/24 | Q4 | 50000 | 19000 | 38 | Behind
Overall results progress: 38.4% (2 outputs, 4 indicators)

## Coverage & Partners
NDMA KnowledgeWeb
Isiolo–Samburu Rangeland Restoration
Counties, sectors, implementers and beneficiaries
Generated 11 Oct 2026 11:29 UTC • by Public portal
Counties
County | Sub-county | Ward
Isiolo | — | —
Samburu | — | —
Sectors
Sector
Environment & NRM
Implementers
Organization
Oxfam
NDMA
Beneficiaries
Group | Targeted | Reached
Agro-pastoralists | 22000 | 9000

## Financing
NDMA KnowledgeWeb
Isiolo–Samburu Rangeland Restoration
Funding sources and county allocations
Generated 11 Oct 2026 11:29 UTC • by Public portal
Funding sources
Funding source | Committed (KSh) | Remarks
Danida | 110000000 | —
Total committed: KSh 110,000,000 • Project budget: KSh 120,000,000